## backlog
Backlog
Id | Assembly | Topic | Description | Status | Phase | Priority
1 | Vaerydian | Binary Heap | finalize binary heap | complete | 1 | NA
2 | Vaerydian | Binary Heap | integrate binary heap in to a-star | complete | 1 | NA
3 | Vaerydian | Quad Tree | add range/distance query to quad tree | complete | 1 | NA
4 | Vaerydian | Quad Tree | update quad tree queries to use range/distance | complete | 1 | NA
5 | Vaerydian | UI | replace timed dialog window with glimpse structures | complete | 2 | NA
6 | Vaerydian | Victory System | need to complete victory system | complete | 3 | 1
7 | Vaerydian | UI | add user interface for gameplay |  | 6 | 4
8 | Vaerydian | UI | make main menu use glimpse - create menu manager in Vaerydian made up of a canvas background and several buttons… use the on-click to determine necessary fucntions… possibly through an event list… | complete | 2 | 1
9 | Vaerydian | Behavior Classes | move behaviors actions into separate classes so a behavior forest can be established |  | 5 | 2
10 | ACB | Agent | flush out agent class | complete | 4 | 2
11 | ACB | APL | setup bus classes to use APL | OBE | 4 | 2
12 | WorldGen | world | need to add rivers |  |  | 3
13 | WorldGen | world | need to define continents |  |  | 3
14 | WorldGen | world | need to define regions |  |  | 3
15 | WorldGen | world | need to populate towns |  |  | 3
16 | WorldGen | world | need to define where caves appear |  | 5 | 2
17 | Vaerydian | Maps | need to define how tranisitions occur between maps |  | 5 | 2
18 | Vaerydian | Itemization | need to build item generator in item factory |  |  | 3
19 | WorldGen | cave | need to elaborate on cave generation |  | 5 | 3
20 | WorldGen | maps | need to elaborate on map definitions (i.e., difficulty, things to find, types of npcs, etc.) |  |  | 3
21 | WorldGen | saving | need to define saving mechanisms |  |  | 4
22 | Vaerydian | saving | need to define saving mechanisms |  |  | 4
23 | Vaerydian | art | need to make character art |  |  | 4
24 | Vaerydian | art | need to make world art |  |  | 4
25 | Vaerydian | itemization | implement "loot drops" |  | 7 | 4
26 | Vaerydian | Abilities | need to implement ablities |  |  | 3
27 | Vaerydian | Affects | need to implement affects |  |  | 3
28 | ACB | Process | implement the bus process class | complete | 4 | 2
29 | ACB | Component | ensure that the IBusComponent class is complete | complete | 4 | 2
30 | Vaerydian | Stats | create and define a stats system |  |  | 4
31 | Glimpse | GButton | update buttons to use color modification and transparancy | complete | 2 | 1
32 | Vaerydian | Skill-Up System | create and define a skill-up system similar to Victory system | complete | 3 | 1
32 | Vaerydian | StartScreen | update menu art |  |  | 4
33 | Vaerydian | Interactions | add interaction enforcement for awards and victories | complete | 3 | 1
34 | Vaerydian | Award system | merge skill and victory handling into one system | complete | 3 | 1
35 | Vaerydian | Award system | add ability to increment attributes | complete | 3 | 1
36 | Vaerydian | Award system | add ability to increment health | complete | 3 | 1
37 | Vaerydian | Templates | need ability to create things from a template of some sort |  | 7 | 3
38 | ACB | BusCommitProcessing | handle issuing commits | complete | 4 | 2
39 | ACB | BusRetrieveProcessing | handle issuing retrieves | complete | 4 | 2
40 | ACB | Bus Processes | handle issuing tasks | complete | 4 | 2
41 | ACB | Bus Processes | handle requesting commits | complete | 4 | 2
42 | ACB | Bus Processes | handle requesting retrieves | complete | 4 | 2
43 | ACB | Bus Registration | handle addition/removal of agents | complete | 4 | 2
44 | Vaerydian | Mouse Reticle | make sure that the mouse reticle is drawn over everything… meaning its drawn last… |  | 6 | 3
45 | WorldGen | maps | generators for other terrain types |  |  | 3
46 | Art | terrain | come up with terrain art |  |  | 4
47 | WorldGen | terrain | come up with color variations for each terrain |  |  | 4
48 | Vaerydian | MapSystem | move world art into pre-load |  | 5 | 2
49 | Glimpse | GButton | update buttons to use text and change the text color on mouse inputs etc. | complete
50 | Glimpse | GButton | correct width calculation bug in buttons |  |  | 4
51 | Vaerydian | UI | character inventory ui |  | 6 | 3
52 | Vaerydian | UI | character stat ui |  | 6 | 3
53 | Vaerydian | NPC Factory | need to create more types of mobs |  |  | 4
54 | Vaerydian | Factories | need to define method for factories to assemble mob templates |  |  | 3
55 | Vaerydian | Systems | Need to define a Trigger system and Trigger Component | complete | 5 | 2
56 | Glimpse | Button | Issue with system thinking unassigned keys are considered pressed | complete

## Sheet3
Assemblies
Vaerydian
WorldGen
ACB
BehaviorLibrary
Glimpse
ECSFramework